## Sheet
ncr_id | date | equipment_tag | clause_id | description | status
NCR-001 | 2026-07-04 | P-101A | 8.5.1 | Product contamination event traced to strainer debris carry-over during monsoon operation; strainer cleaning interval under review against seasonal load. | open
NCR-002 | 2026-06-17 | CV-301A | 7.1.5 | Flow control valve stroke-test record expired; measurement traceability broken for acceptance decisions on feed flow. Recalibration scheduled. | open
NCR-003 | 2026-02-12 | P-102A | 10.2 | Repeat vibration corrective work without root cause determination; fourth occurrence in twelve months escalated for RCA. | open
NCR-004 | 2025-11-24 | HX-201B | 8.7 | Off-spec product temperature during exchanger fouling; batch segregated and reprocessed. Closed after cleaning per SOP-105. | closed
NCR-005 | 2025-09-05 | P-101B | 8.1 | Preventive maintenance interval missed during outage congestion; risk assessment completed, no product impact found. | closed
NCR-006 | 2025-06-17 | CV-303A | 9.1 | Monthly KPI computation gap for utilities makeup process; reporting restored. | closed